## Stakeholder Matrix
Sl.No | Stakeholder Name | Contact Information | Impact to Project | Influence to Project | Whats Important to stakeholder | How stakeholder can contribute | How can stakeholder derail the project | Engage the stakeholder
1 | Google and Apple app store | Mark Tiffany Mark.tiffany@google.com Phone No.:- (+1) 418-625-8966, David Jones David.jones@apple.com Phone No.:- (+1) 431-795-2317 | High | Supplier | Number of user downloads, Software updates | Hassle free downloads, App promotion to display in top picks and on home page | Removal of application from store, gliches during downloads and installation, not promoting in top list | Increasing the user base, regular software updates
2 | Tour guide Community(American tour guide society) | John Elen John.elen@tgc.com Phone No.:- (+1) 781-575-6129 | Medium | Supplier | Providing regular business, and tour guide package promotions | Providing best in class tour guides and services | Last minute cancellations, providing bad experience to travellers | Providing regular business, feedback and reviews, incentives for good service
3 | Rental services(Kyte, Avis, Enterprise) | Mark Lee Mark.lee@kyte.com Phone No.:- (+1) 321-6301-6103, Park Joo Park.joo@avis.com Phone No.:- (+1) 651-506-601 | High | Supplier | Regular bookings and accurate commission values | Providing the best cars size and comfort ranges, break down assistance and accurate data on availability | Last minute cancellation of bookings, exit from platform | Transparent feedback and reviews, analytics related business
4 | Hotel Franchises(Hilton, Marriott) | Jack Miles Jack.miles@hilton.com Phone No.:- (+1) 801-125-7929, Juliet Olive Juliet olive@mariott.com Phone No.:- (+1) 881-470-5199 | High | Supplier | Accurate finacial model and cost breakdown, regular bookings, transparent reviews and feedbacks | Providing the best services, accurate room availability data and best offers/deals | Providing lesser amenities than listed, bad service and last minute cancellations | Listing publicity and marketing based on feedback and reviews, user engagement analytics
5 | Google Maps and Weather | William Miles William miles@google.com Phone No.:- (+1) 381-175-9529 | High | Supplier | Number of users and time spent on app | Providing route maps, real time weather updates, traffic data | Inaccurate data related to traffic and weather | Integration onto the platform, providing customer usage data and analytics
6 | Marketing Agency(Social Media Marketing included) | Emmett Oscar Emmett.oscar@A1marketing.com Phone No.:- (+1) 281-905-6259 | Medium | Media | Helping the agency in their growth in the industry | Customer engagement and acquisition strategies, Evaluation of current marketing strategies | Ineffective marketing strategies | Providing continuous business and market development inputs, Customer engagement reports
7 | Payment Services | James Lucas James.lucas@applepay.com Phone No.:- (+1) 881-365-0428, Robert Liam Robert.liam@paypal.com Phone No.:- (+1) 451-775-3220 | High | Supplier | No of users(App traffic), payment process reviews and feedback | Hassle free service, information related to software updates, any promotional coupons or cashback info, maintaing privary and info security standards | Glitches during payment processing, privacy and security gaps | User engagement analytics, service usage feedback
8 | Department of Tourism | Wilson Aldo Wilson.aldo@doft.com Phone No.:- (+1) 876-735-8631 | Low | Government Agency | Number of travellers/tourists | Accurate information about slot availability, visting hours and dates, and customer service. | Inaccurate data about visiting hours, closures and slot availability | Reports related to visitor bookings, financial model and forecasting/prediction of upcoming visitors
9 | Investors(Venture Capital, Angel investors) | Taylor Evans Taylor.evans@apexcapital.com Phone No.:- (+1) 883-185-1929 | High | Capital Providers | Return on investment | Funding, Business Guidance, Helping connect with brands and associations | Fund restriction, Downvoting important business decisions | Regular board meetings, updates on product development and business